## Summary
IOS App Release testing - IOS App Test Suite v2.2.8 (SmartShade v5.0.2 & SmartCurtain v2.0.8 & SmartBridge 4.3.0 bnrf 3.11.0) |  |  |  |  | Date: 01-05-2025
Code | Test Cases | Date | Pass / Fail | File Name | Remark
AX | Account | 06-05-2025 | Pass
AX01 | ValidLogInOut | 01-05-2025 | Pass | IOS_App_Test_Suite_v2.2.8_Account_Part1_01May2025
AX02 | InvalidLogInOut | 06-05-2025 | Pass | Manually tested
AX03 | ValidSignUp | 01-05-2025 | Pass | IOS_App_Test_Suite_v2.2.8_Account_Part1_01May2025
AX04 | InvalidSignUp | 06-05-2025 | Pass | Manually tested | Reset app got an error from Appium, but it is fine.
AX05 | ValidChangePassword | 05-05-2025 | Pass | Manually tested
AX06 | ValidViewProfile | 01-05-2025 | Pass | IOS_App_Test_Suite_v2.2.8_Account_Part1_01May2025
AX07 | ValidForgetPassword | 05-05-2025 | Pass | Manually tested
AX08 | InvalidLogInCapital | 01-05-2025 | Pass | IOS_App_Test_Suite_v2.2.8_Account_Part1_01May2025
BX | Bridge | 06-05-2025 | Pass
BX01 | Valid PairBridge (OCR) | 01-05-2025 | Pass | IOS_App_Test_Suite_v2.2.8_Bridge_Part1_01May2025
BX02 | Valid PairBridge Offline (OCR) | 01-05-2025 | Pass | IOS_App_Test_Suite_v2.2.8_Bridge_Part2_01May2025 | Checked that pair to correct bridge
BX03 | Invalid PairBridge Local (OCR) | 01-05-2025 | Pass | IOS_App_Test_Suite_v2.2.8_Bridge_Part2_01May2025 | The error message wasn't captured due to the message timeout. It's fine.
BX04 | Invalid PairBridge Wifi Off (OCR) | 01-05-2025 | Pass | IOS_App_Test_Suite_v2.2.8_Bridge_Part2_01May2025
BX05 | Valid CheckBridgeInfo | 01-05-2025 | Fixed | IOS_App_Test_Suite_v2.2.8_Bridge_Part2_01May2025 | Not able to change the Bridge name. After changing the bridge name, the bridge name shows correctly in the settings page and dashboard. After a few seconds or attempts, the bridge name suddenly changed back to "ATTS"
BX06 | Valid PairDualBridges | 05-05-2025 | Pass | Manually tested | Frirst Bridge Bonjour turn off and still able to scan
BX07 | Cloud CheckBridgeInfo | 01-05-2025 | Fixed | IOS_App_Test_Suite_v2.2.8_Bridge_Part3_01May2025 | Not able to change the Bridge name. After changing the bridge name, the bridge name shows correctly in the settings page and dashboard. After a few seconds or attempts, the bridge name suddenly changed back to "ATTS"
BX08 | Cloud AddUser | 01-05-2025 | Fixed | IOS_App_Test_Suite_v2.2.8_Bridge_Part3_01May2025 | Added user in local mode. After changing to cloud mode, the user list becomes empty.
BX07 | Invalid PairManualIP
BX08 | Valid PairManualIP
BX11 | Invalid DeleteBridge | 01-05-2025 | Pass | IOS_App_Test_Suite_v2.2.8_Bridge_Part3_01May2025
MX | Menu | 06-05-2025 | Pass
MX01 | ValidSubmitInstaBugReport | 01-05-2025 | Pass | IOS_App_Test_Suite_v2.2.8_Menu_Part1_01May2025 | No "done" in virtual keyboard due to IOS problem. It's fine
MX02 | ValidNavigateMenu | 05-05-2025 | Pass | Manually tested
MX03 | ValidPairBridgeEmptyDashboard | 05-05-2025 | Pass | Manually tested
SX | SmartShade | 06-05-2025 | Pass
SX01 | Valid Control Position - Sign In | 02-05-2025 | Pass | IOS_App_Test_Suite_v2.2.8_Shade_Part1_02May2025 | The direction of the editing position is converted with the slider. Confirmed with Jakub it is accepted for now if the direction and shade movement is the same.
| Sign Out | 06-05-2025 | Pass | Manually tested
SX02 | Invalid UncalibrateShade | 02-05-2025 | Pass | IOS_App_Test_Suite_v2.2.8_Shade_Part3_02May2025
SX03 | Valid CheckShadeInfo | 02-05-2025 | Pass | IOS_App_Test_Suite_v2.2.8_Shade_Part2_02May2025
SX04 | Invalid RenameWeirdNames | 02-05-2025 | Pass | IOS_App_Test_Suite_v2.2.8_Shade_Part2_02May2025
SX05 | Cloud ControlPosition | 02-05-2025 | Pass | IOS_App_Test_Suite_v2.2.8_Shade_Part2_02May2025 | The direction of the editing position is converted with the slider. Confirmed with Jakub it is accepted for now if the direction and shade movement is the same.
SX06 | Valid ControlSpeeds | 02-05-2025 | Pass | IOS_App_Test_Suite_v2.2.8_Shade_Part4_02May2025
SX07 | Valid FWForceUpdate | 02-05-2025 | Fixed | IOS_App_Test_Suite_v2.2.8_Shade_Part5_02May2025 | After the shade update is completed, the shade becomes empty. Besides, after the update is finished, the app redirects the user to the Connect Bridge or Bluetooth page instead of setting up (Configuration).
SB01 | Invalid PairNoneShade | 06-05-2025 | Pass | Manually tested
SB02 | Valid ControlPosition | 06-05-2025 | Pass | IOS_App_Test_Suite_v2.2.8_Shade_Part6_06May2025 | The direction of the editing position is converted with the slider. Confirmed with Jakub it is accepted for now if the direction and shade movement is the same. Manually tested (pair BLE shade)
SB03 | Valid SpeedControl | 06-05-2025 | Pass | Manually tested | Slower speed = 29.5s, faster speed = 22.5s
SB04 | Valid FWForceUpdate | 06-05-2025 | Fixed | Manually tested | After the shade update is completed, the shade becomes empty. Besides, after the update is finished, the app redirects the user to the Connect Bridge or Bluetooth page instead of setting up (Configuration).
CX | SmartCurtain | 06-05-2025 | Pass
CX01 | Valid Check Curtain Info | 05-05-2025 | Pass | IOS_App_Test_Suite_v2.2.8_Curtain_Part1_05May2025
CX02 | Valid Position Control | 05-05-2025 | Pass | IOS_App_Test_Suite_v2.2.8_Curtain_Part1_05May2025
CX03 | Valid Speed Control | 05-05-2025 | Pass | IOS_App_Test_Suite_v2.2.8_Curtain_Part2_05May2025
CX04 | Invalid Uncalibrated Curtain Pair
CX05 | Cloud Check Curtain Info | 06-05-2025 | Pass | Manually tested | Not allow "Edit Devices", "Calibrate", "Speed Setting"
CX06 | Cloud Position Control | 06-05-2025 | Pass | Manually tested (CX06_Cloud Position Control)
CX07 | Invalid Cloud Speed Control | 06-05-2025 | Pass | Manually tested
CG01 | Valid Group ControlPositions | 06-05-2025 | Pass | Manually tested (CG01_Valid Group ControlPositions)
CR01 | Valid Routine ControlPositions | 06-05-2025 | Pass | Manually tested (CR01_Valid Routine ControlPositions)
CB01 | Invalid PairNoneCurtain | 05-05-2025 | Pass | IOS_App_Test_Suite_v2.2.8_Curtain_Part4_05May2025
CB02 | Valid Position Control | 05-05-2025 | Pass | IOS_App_Test_Suite_v2.2.8_Curtain_Part4_05May2025
CB03 | Valid Speed Control | 06-05-2025 | Pass | Manually tested (CB03_BLE_Speed_Control)
CB04 | Valid OTA Update
GX | Group | 03-05-2025 | Pass
GX01 | Valid CreateGroup | 03-05-2025 | Pass | IOS_App_Test_Suite_v2.2.8_Group_Part1_03May2025
GX02 | Invalid DuplicateGroup | 03-05-2025 | Pass | IOS_App_Test_Suite_v2.2.8_Group_Part2_03May2025
GX03 | Valid RenameGroup | 03-05-2025 | Pass | IOS_App_Test_Suite_v2.2.8_Group_Part1_03May2025
GX04 | Valid ControlPositions | 03-05-2025 | Pass | IOS_App_Test_Suite_v2.2.8_Group_Part3_03May2025
GX05 | Valid RemoveGroupDevice | 03-05-2025 | Pass | IOS_App_Test_Suite_v2.2.8_Group_Part1_03May2025
RX | Routine | 06-05-2025 | Pass
RX01 | Valid CreateRoutine - Sign In | 06-05-2025 | Pass | Manually tested
| Sign Out | 04-05-2025 | Pass | IOS_App_Test_Suite_v2.2.8_Routine_Part1_04May2025
RX02 | Invalid DuplicateRoutine | 04-05-2025 | Pass | IOS_App_Test_Suite_v2.2.8_Routine_Part1_04May2025
RX03 | Valid CheckDashboard
RX04 | Valid CreateMaxCapacility | 04-05-2025 | Pass | IOS_App_Test_Suite_v2.2.8_Routine_Part1_04May2025
RX05 | Valid CreateSunrise | 04-05-2025 | Pass | IOS_App_Test_Suite_v2.2.8_Routine_Part2_04May2025
RX06 | Valid CreateSunset | 04-05-2025 | Pass | IOS_App_Test_Suite_v2.2.8_Routine_Part2_04May2025
RX07 | Valid CheckSuntime_Dashboard | 06-05-2025 | Pass | Manually tested (RX07_CheckSuntime)
RX08 | Valid ChangeTimezone | 06-05-2025 | Pass | Manually tested (RX08_ChangeTimezone)
CS | CloudSync | 06-05-2025 | Fail
CS01 | Valid UpdateGearPower | 06-05-2025 | Fail | IOS_App_Test_Suite_v2.2.8_CloudSyn_06May2025 | Dashboard didn't update Shade power (CloudSyn delay = 60s)
CS02 | Valid UpdateShadePosition | 06-05-2025 | Fail | IOS_App_Test_Suite_v2.2.8_CloudSyn_06May2025 | Position not updates in Dashboard (CloudSyn delay = 60s)
CS03 | Valid UpdateBridgePower | 06-05-2025 | Fail | IOS_App_Test_Suite_v2.2.8_CloudSyn_06May2025 | Dashboard didn't update Bridge power (CloudSyn delay = 60s)
OT | OTA | 06-05-2025 | Pass
OT01 | Valid Update Shade FW | 06-05-2025 | Pass | Manually tested | From 3.11.6 to 5.0.2
OT02 | Invalid PowerInterrupt | 06-05-2025 | Pass | Manually tested
Major Issue in IOS v2.2.8:
1. The app cannot change the Bridge name, and add user -> Fixed
2. Shade FW Updates required twice for pairing, but it was already added into the dashboard when the first pairing finished. -> Fixed
3. The direction of the editing position is converted with the slider. Confirmed with Jakub it is accepted for now if the direction and shade movement is the same.
4. CloudSyn fail with 60 second delay for Shade & Bridge Power